## Production Plan
|  |  |  | Production Plan | [28 empty] | FM03 Rev.01 Ref.EN-P-01
Status | WW | DATE Record | Product P/N | MODEL | QTY | SYN Requestor | PM | Customer | Expected | Revised | OK/DAY | Total NG | Total OK | Yield | DONE | 4M Check |  |  |  | PD Plan | [6 empty] | QA |  | Store | SC | PD PIC | Team | Remark
[7 empty] | Work Order | [8 empty] | Man | Mac | Med | Mat | PCBA | BBAS | TEST | RMA | PREP | PD Start | PD Finish | Sampling% | QA Finish | Received date | Mat'l coming
Done | 22 | 01/06/2026 | 1E7D25403001 | Water Level Rice - BBAS | 200 | K.Ploy | WO-2026-001 | Toyota TH | 13/06/2026 |  | 40 | 2 | 198 | 99% | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |  |  | 02/06/2026 | 11/06/2026 | 100 | 12/06/2026 | 12/06/2026 |  | Noi | 3 | ส่งครบ
On process | 24 | 10/06/2026 | 1E6D25234000 | SMARTNAV - BBAS | 150 | K.Boss | WO-2026-002 | Honda Mfg | 20/06/2026 |  | 21 | 1 | 147 | 99% |  |  |  |  | ✓ | ✓ | ✓ |  |  |  | 12/06/2026 | [5 empty] | Kiert | 2
Mat'l coming | 25 | 13/06/2026 | 1E4D26458000 | CM2 Battery - PCBA | 80 | K.Aun |  | AISIN | 28/06/2026 |  | 0 | 0 | 0 | [16 empty] | Components (Consign) | Au | 2 | รอ consign part