## Sheet1
|  |  |  | Production Plan | [24 empty] | FM03 Rev.01 Ref.EN-P-01
Status | WK | DATE Record | Product P/N | MODEL | QTY | SYN Requestor | PM | SC | 4M Check |  |  |  | PD Plan |  |  |  |  | QA |  | Store | Expected date | Revised date | DONE | PD PIC | Team Member | OK/DAY | TOTAL NG | TOTAL OK | Remark
[7 empty] | Work Order. | Mat'l coming | Man | Mac | Med | Mat | PCBA | BBAS | TEST | Start date | Finish date | Test rate% | Finish date | Received date
| 36 | 2025-09-02 | 1E7D25403001 | Water Level Rice - BBAS (RMA) | 53 | PM DEW | 102026 | - | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | 2026-02-18 | - | - | - | - | 2026-02-25 | - | - | Noi,Kiert | 2 | - | - | 21 | ประกอบงานส่ง 6 pcs. สำหรับส่งงานวันที่ 18 Feb 2026
| 2 | 2026-01-05 | 1E6D25234000 | SMARTNAV_SMARTNAV - BBAS (Prototype) | 55 | PM DEW | - | - | FALSE | FALSE | TRUE | TRUE | FALSE | TRUE | TRUE | 2026-04-10 | - | - | - | - | 2026-03-31 | 2026-06-12 | - | Noi,Kiert | 2 | - | - |  | อยูู่ในขั้นตอนการรอวัตถุดิบเข้า
| 2 | 2026-01-05 | 1E6D25234001 | SMARTNAV_RSU - BBAS (Prototype) | 55 | PM DEW | - | Components | FALSE | FALSE | TRUE | TRUE | FALSE | TRUE | TRUE | 2026-04-22 | - | - | - | - | 2026-03-31 | 2026-06-12 | - | Noi,Kiert | 2 | - | - | - | อยูู่ในขั้นตอนการรอวัตถุดิบเข้า
| 4 | 2026-01-23 | 510L0124E011 | YG850-081A - Jig Test (Maintenance) | 1 | PM MIE | - | - | FALSE | FALSE | TRUE | TRUE | FALSE | TRUE | TRUE | - | - | - | - | - | - | - | - | - | - | - | - | - | -
| 13 | 2026-03-26 | - | 5K45_HI - SEMI ASSEMBLE | 133 | PM DEW | - | Consign part | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE | FALSE | 2026-05-08 | - | - | - | - | 2026-06-30 | - | - | Kiert,Noi | 2 | - | - | 95 | รอ Consign part ในการประกอบ Semi
| 13 | 2026-03-26 | - | 5K45_LO - SEMI ASSEMBLE | 137 | PM DEW | - | Consign part | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE | FALSE | 2026-05-08 | - | - | - | - | 2026-06-30 | - | - | Kiert,Noi | 2 | - | - | 37 | รอ Consign part ในการประกอบ Semi
| 17 | 2026-04-23 | 1E5D25403001 | Water Level Rice - PCBA sensor | 37 | PM DEW | 192026 | Components | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE | TRUE | 2026-05-18 | - | - | - | - | 2026-06-30 | - | - | Run,Kiert,Noi | 1 | - | - | 21 | แบ่งบางส่วนทำ R&D, รอเปิดซื้อ Components
| 17 | 2026-04-23 | 1E5D00364000 | IOT Gateway - PCBA (New design) | 3 | PM OHM | - | Components | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | 2026-06-08 | 2026-06-09 | - | - | - | 2026-06-10 | - | - | Run | 1 | - | - | - | รอ Components, พี่รันประกอบ PCBA
| 18 | 2026-04-29 | 103L0164C005-BOI | Daughter board Version 2.0 - PCBA | 20 | PM KRADOOM | - | Components | FALSE | FALSE | TRUE | TRUE | TRUE |  | TRUE | - | - | - | - | - | - | - | - | Run,Noi | 2 | - | - | - | รอแผนงานกำหนดการผลิตจาก PM
| 18 | 2026-04-29 | 103L0164C002-BOI | Light Module Version 2.3 (Receiver) - PCBA | 20 | PM KRADOOM | - | Components | FALSE | FALSE | TRUE | TRUE | TRUE |  | TRUE | - | - | - | - | - | - | - | - | Run,Noi | 2 | - | - | - | รอแผนงานกำหนดการผลิตจาก PM
| 19 | 2026-05-06 | - | Water Levei Rice - 3D Print Enclosure (CAP insert) | 2300 | PM DEW | 182026 | - | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | FALSE | 2026-05-06 | 2026-06-20 | - | - | - | 2026-06-30 | - | - | - | - | - | - | 2100 | ขึ้น 3D filament
| 19 | 2026-05-06 | 205TBBAS0411 | Water Levei Rice - Assemble CAP insert | 2300 | PM DEW | 182026 | - | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | TRUE | 2026-05-11 | 2026-06-11 | - | - | - | 2026-06-30 | - | - | Run,Kiert,Noi | 3 | - | - | 2100 | ประกอบชุดใส่ Capacitor ของงาน Water Level Rice
| 22 | 2026-05-29 | 1E4D26458000 | CM2-AAA-Battery - PCBA | 50 | PM DEW | 212026 | Components (Consign) | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | 2026-06-10 | - | - | - | - | 2026-06-23 | - | - | Run | 1 | - | - | - | รอ Consign part ในการประกอบ PCBA
| 23 | 2026-06-03 | - | 5K45 - DEPANEL | 1802 | PM DEW | - | PCBA (Consign) | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE | FALSE | 2026-06-10 | - | - | - | - | Jun'26 | - | - | Kiert,Au,Yui,Sai | 4 | - | - | -
| 24 | 2026-06-12 | 103L0033T012-BOI | E13A_STD - RE-TEST | 718 | PM KRADOOM | 162026 | - | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | 2026-06-12 | - | - | - | - | 2026-06-19 | - | - | Nile,Kiert | 1 | - | - | 300 | ทดสอบสีไฟ LED